## Sample
Project Status Matrix
WEEKLY STAFFING
|  | Status | FTE | Sofie | Catherine | Nelima | Jessica | Raksha | Thoang | Saori | Bona | Thuy | Kevin | KC | Meetu | Remarks / Notes
| UTILIZATION |  |  | 100% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 0% | 0% | 10% | Yuning - Maternity Leave till 17 Oct Phoo Remote Work in Indonesia - 29 Sep to 15 Oct Li Ji - Remote Work -06 Oct to 10 Oct Kay & Arghya - 6 Oct
| Vacation/Medical/Holiday | [6 empty] | 20% | [6 empty] | 10% | Law - Reservist (06 -17 Oct) Christina - 06 Oct (AM) Sushi - 07 Oct Cath - 09 - 10 Oct (Course) Raksha - 9 Oct (off in-lieu) Phoo - 06 Oct (MC) Meetu - 08 Oct (PM)
CODE | PROJECT NAME
Architecture Department
| 00120.068 Regional SE Asia Admin | Active | 2.4 | 80% | 60% | 100% | [9 empty] | Brinda & Neha- Staffing calls + Portfolio updates Nelima - 50 (SG) + 50 (Dubai) Mayapada Invoices - Add Fee
| 00220.068 Regional Marketing SE Asia | Active | 1.7 | 20% |  |  | 20% | 30% | 10% | 60% | 20% | 10% |  |  |  | Marketing Collaterals Update - Raksha, Thoang Microsite Updates - Saori, Raksha, Jess HKS 5 Nov event planning - Saori, Bona, Jess, Raksha, Sofie PR & Linkedin - Saori, Raksha SUSS RFP - Jess, Gordon, Manon
| 00250.068 Regional Marketing Health | Active | 0.7 |  |  |  | 20% | 30% |  |  | 20% |  |  |  |  | Aus Presentation Deck (for Angela) - Saori Follow up on Proposals Update Interview/ Presentation templates - Raksha
| 00120.209 Regional Melbourne Administration | Active | 0
| 00220.209 Regional Marketing Melbourne | Active | 0.2 | [6 empty] | 20% | [5 empty] | NZ RHRP D&B - Michael, Joey, Jessica, Angela Logan City Council Follow-up - Michael, Jessica Gold Coast Hospitality Towers - Michael, Andrew Life Science in Aus - Manon, Michael, Jess
Architecture Department
| 00267.068 Sector Marketing SE Asia MC | Active | 0
| 25691.000 Stack Hayward SVY03 | Active | 0
| 25706.000 Digital Realty 1204 Alma DC | On Standby | 0
| 25825.000 Ascent ATL Campus Expansion | inactive | 0
| 25992.000 Project Inabi | On Standby | 0
| 24695.009 PHX02 Edgeconnex | On Standby | 0
| 25313.006 Aligned PHX07 | On Standby | 0
| 26633.000 IAD04 | Active | 0
| 26282.000 Project NEO | On Standby | 0
| 26233.110 JAN100 | Active | 0
| 26233.120 JAN101 | Active | 0
| 26233.130 JAN102 | Active | 0
| 26233.140 JAN103 | Active | 0
| 26233.160 JAN104 | Active | 0
| 26233.150 JAN100 ACB | Active | 0
| 26233.190 JAN105 | Active | 0 | [12 empty] | IFC Submission 26 Sep
| 26233.200 JAN106 | Active | 0 | [12 empty] | IFC Submission 26 Sep
| 26233.210 JAN107 | Active | 0 | [12 empty] | IFC Submission 26 Sep
| 26233.220 JAN108 | Active | 0 | [12 empty] | IFC Submission 26 Sep
| 26233.230 JAN109 | Active | 0 | [12 empty] | IFC Submission 26 Sep
| 26233.240 JAN110 | Active | 0 | [12 empty] | IFC Submission 26 Sep
| 26233.250 JAN111 | Active | 0 | [12 empty] | IFC Submission 26 Sep
| 26233.260 JAN105 AWB | On Standby | 0
| PIF Saudi AI Competition | On Standby | 0
Hospitality
| 00151.068 Admin SE Asia Hospitality | Active | 0.1 | [6 empty] | 10% | [5 empty] | Jiake - Charrette
| 00251.068 Regional Marketing Hospitality | Active | 1.3 |  |  |  | 30% |  | 80% |  |  | 20% |  |  |  | Sebana Cove, Johor – Master Plan strategic overview for presentation to Chairman Tourism Plan, Fiji – possible Master Plan strategic overview HDMon Van Don Clubhouse RFP Diriyah Wadi Arts+IT City Hanoi Hospitality Microsites - Saori Global India proposals - Jess, Thoang CTI Vegacity - Thuy, Jess
| 60068.000 U Bo Peak | Active | 0.2 | [8 empty] | 20%
| 60070.000 Sun Agribank Tower | Active | 0 | [12 empty] | to close signed agreement
| 60072 Banyan Tree Manila - Design Review | Active | 0
| 40256.999_Al Dhannah Masterplan | Active | 0
Life Science
| 00175.068 Admin SE Asia Life Science | Active | 0 | [12 empty] | Lab Asia Tina-ISPE
| 00275.068 Regional Marketing Life Science | Active | 0.1 | [6 empty] | 10% | [5 empty] | Microsite for Life Science - Saori, Manon
| 60058.000 STA | Active | 0 | [12 empty] | NEED RENDERING FOR THIS WEEK (6-7 views :HPLC, common corr, trouble shooting)
| 60059.000 NUS SRB | Active | 0 | [12 empty] | NEED RENDERING for following week
| 40245.996 Abu Dhabi Plant Tissue Lab | Active | 0
| 60063.000 A*Star Biomed | Active | 0
| 60071.000 HTX Forensic Lab | Active | 0
Active Projects
| 00254.068 Sector Marketing SE Asia Education | Active | 0
| 00252.068 Sector Marketing SE Asia Sports | Active | 0.15 |  |  |  | 5% |  | 10% | [6 empty] | Hanoi Sports Stadium RFP from T&T
| 60028.000 Healthway Day Surgery Center | Active | 0
| 60160.000 Changi General Hospital Remodel | Active | 0
| 60040.000 CGH Remodelling - Variation Studies | Active | 0
| 60055.000 Tan Tock Seng Ambulatory | Active | 0.3 |  |  |  | 10% | 20% | [7 empty] | Subconsultancy Agreement - Jess, David HKS ID Scope & Fee with CIAP - Jess, David
| 60054.000 NUHR Phase 1 | Active | 0.1 |  |  |  | 10% | [8 empty] | Portfolio Setup, BIM contract finalisation
| 60212.000 Eastern General Hospital | Active | 0 | [12 empty] | Post tender comments (UGM)
| 40158.000 MoH Hospital Projects | Active | 0
| 40176.000 Al Abnaa Office | Active | 0 | [12 empty] | Model Handover for DD + Animation (VO-3)
| 40182.000 FAKEEH Medical hospital in Ubhor Jeddah | Active | 0 | [12 empty] | handover
| 60046.000 Mayapada Apollo Batam Int'l Hospital | Active | 0 | [12 empty] | Layouts finalized 30 Sept
| 60037.000 HBCHRC ( ICICI Tata) | On Standby | 0
| 60043.000 KKIP Masterplan | On Standby | 0
| 60043.000 KKIP - Development Masterplan & Renders | On Standby | 0
| 60048.003 Reliance Interior renovation- med planning | Active | 0
| 60048.002 Reliance Interior renovation- interiors (mood boards) | Active | 0
| 60051.000 Queensway Node | Active | 0 | [12 empty] | Invoicing
| 60065.000 Expedia India | Active | 0 | [12 empty] | DD Stage submission 03 Oct
| 40186.000 Novacare Hospital Islamabad | On Standby | 0 | [12 empty] | ID Comments, Additional Fees Addendum and Invoice Follow Up
| 60230.001 Apollo Chennai Hospital Concept Planning - Add Service - Shelved | On Standby | 0 | [12 empty] | Payment follow up
| 25705.000 UC Davis Health Design (California - Health Interiors) | On Standby | 0
| Gold Coast Convention Center | On Standby | 0
| 60155.000 Riphah Islamabad Hospital | On Standby | 0 | [12 empty] | Client rep requested for meetings to resume work
| 40236.000 LAU Masterplan Visioning | Active | 0
| 40209.000 KCH Casablanca Morroco | Active | 0 | [12 empty] | SD stage- workshop on 30 Oct ,31 October, 1st november
| 40246.000 Prince MBS Center for Autism | Active | 0
| 60060.000 Reliance Hospital, Jamnagar | Active | 0
| 60053.000 Reliance Hospital, RCP, Navi Mumbai | Active | 0
| 60064.000 Reliance Kanchangauri - Neuro Ortho | Active | 0
| 60034.000 Adani Medicity interior design | Active | 0
| 60066.000 RSPI Expansion Tower Jakarta | Active | 0.2 | [7 empty] | 20%
| 40201.000 CCAD CARBON ION DESIGN | Active | 0
| 27268.000 Mayo Clinic Arizona | Active | 0 | [12 empty] | Workshop 8 Oct
| 40253.000 Peninsula Medical Center Peer Review | Active | 0
| 40252.000 Bedfordview Day Hospital | Active | 0
| 40258.000 Al Shifa Eye Centre | Active | 0 | [12 empty] | GROUNDBREAKING 20 OCTOBER
| 40239.000 Al Murjan Healthcare Masterplan in Jeddah | Active | 0 | [12 empty] | Masterplan Package due December
| 60069.000 NHCI_DATSAS Multispecialty Hospital Nagpur | Active | 0.4 | [7 empty] | 40%
| 40218.000_Qatar College of Dental and Nursing | Active | 0
| AIA Hong Kong Park | Active | 0
ACTIVE PURSUITS - WILL CHARGE HOURS TO (NEED TO UPDATE)
| 40144.996 King College Hospital - Cairo, Egypt | On Standby
| 40148.999 Libya American Medical City | Active
| MSE New Office | Active
| Jakarta Waterfront | On Standby
| 60220.999 US Bangla Hospital | On Standby
| 40130.996 MedTech Medical City (RIVA) | On Standby
| 00274.010 Jakarta Senior Living | On Standby
| 60222.999 Hyderabad Hospital with Integrated Medical College | On Standby
| 90273.996 Fujian Anta Hemin Hospital (Competition) | On Standby
| 60224.999 Ranna Resorts in Sri Lanka | On Standby
| 60225.999 Lahore CBD Master plan | On Standby
| Lahore Block 3 CBD | On Standby
| 40139.996 Rawasi Jabal Omar | On Standby
| EGYPT hospital (university hospital 200 beds) | On Standby
| EGYPT hospital (350 beds) - CAIRO | On Standby
| 60229.999 Petra University Faculty of Medicine | On Standby
| 00120.068 Cambodia | on Standby
| 60039.999 Amman Design Management | On Standby | 0
| 60038.999 KSB Wave Pool Complex | On Standby | 0
| 63004.996 Parkville Hospital | Active | 0
| 60056.999 Kallang Alive Indoor Arena | Active | 0.05 |  |  |  | 5% | [8 empty] | Tender Closing 21 November; London team visiting Singapore 6-10 Oct
| 60049.999 KCH New Delhi | On Standby | 0
| 40220.996 KCH Dubai Phase II RFP | On Standby | 0 | [12 empty] | Waiting for final results
| 40231.996 Tabuk Airport | Active | 0
| 40232.996 American Hospital Science Park | On Standby | 0
| Abu Dhabi Stem Cell Center | On Standby | 0
| 40235.996 200 Bed DOC Medical Center - Addis Ababa (Ortho) | On Standby | 0
| 40234.996 Dubai Festival City HealthHub Hospital | On Standby | 0
| 40215.996 New Renal Hospital, Oman | On Standby | 0 | [12 empty] | submitted
| 40214.996 King Saud Medical City | On Standby | 0 | [12 empty] | submitted
| 40216.996 Renovation & Expansion Construction Works at Tawam Hospital | On Standby | 0
| 40174.996 Alameda Cleveland Clinic Hospital | On Standby | 0
| 40217.996 Al Duqm Hospital Oman | On Standby | 0
| 40219.996 Royal Hospital Oman | On Standby | 0
| 40222.996 NHDD -Cardiac Hospital | On Standby | 0
| 40221.996 DHCC Hospital | On Standby | 0
| 40224.996 Al Seeb Hospital at Sultan Haitham City | On Standby | 0
| 40223.996 Education City Stadium Legacy Design, Doha | On Standby | 0
| 40225.996 Facility Facelift Enhancement Projects | On Standby | 0
| 40227.996 TSEMEX Hospital | On Standby | 0
| 40226.996 Moorefield Eye Hospital | On Standby | 0
| 40229.996 Qiddiya IHN | On Standby | 0 | [12 empty] | Proposal Submitted
| 60057.999 UWCSEA Tengah Campus | Active | 0
| 40237.996 National rehab and Wellness Oman | On Standby | 0
| 40238.996 Dao Ben Ghayadh | On Standby | 0
| 27219.996 Chennai Hackathon | Active | 0
| 40240.996 SAMI Masterplan and Architecture, KSA | Active | 0
| 40241.996 MODON Masteplan | Active | 0
| 45001.996 Dalma Island Hospital - Abu Dhabi | Active | 0
| OUD Al Nakheel Residential Development | Active | 0
PROJECTS
Active
Not Yet Started
Hold
Cancelled
Completed
Not Awarded
On Standby

## BLANK
Project Status Matrix
WEEKLY STAFFING
|  | Status | FTE | [12 empty] | Remarks / Notes
| UTILIZATION |  |  | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 10%
| Vacation/Medical/Holiday | [6 empty] | 20% | [6 empty] | 10%
CODE | PROJECT NAME
Architecture Department
| 00267.068 Sector Marketing SE Asia MC | Active | 0
| 25691.000 Stack Hayward SVY03 | Not Yet Started | 0
| 25706.000 Digital Realty 1204 Alma DC | Not Yet Started | 0
| 25825.000 Ascent ATL Campus Expansion | Not Yet Started | 0
| 25992.000 Project Inabi | Not Yet Started | 0
| 24695.009 PHX02 Edgeconnex | Not Yet Started | 0
| 25313.006 Aligned PHX07 | Not Yet Started | 0
| 26633.000 IAD04 | Not Yet Started | 0
| 26282.000 Project NEO | Not Yet Started | 0
| 26233.110 JAN100 | Not Yet Started | 0
| 26233.120 JAN101 | Not Yet Started | 0
| 26233.130 JAN102 | Not Yet Started | 0
| 26233.140 JAN103 | Not Yet Started | 0
| 26233.160 JAN104 | Not Yet Started | 0
| 26233.150 JAN100 ACB | Not Yet Started | 0
| 26233.190 JAN105 | Not Yet Started | 0
| 26233.200 JAN106 | Not Yet Started | 0
| 26233.210 JAN107 | Hold | 0
| 26233.220 JAN108 | Not Yet Started | 0
| 26233.230 JAN109 | Not Yet Started | 0
| 26233.240 JAN110 | Not Yet Started | 0
| 26233.250 JAN111 | Not Yet Started | 0
| 26233.260 JAN105 AWB | Not Yet Started | 0
| PIF Saudi AI Competition | Not Yet Started | 0
Not Yet Started
Active
Not Yet Started
Hold
Cancelled
Completed
Not Awarded
On Standby